### 📋 The Milestone List (12 Weeks)

**Month 1: The Brain (Data, Graphs, and GNN)**

*   **Week 1:** Environment Setup, PostgreSQL Baseline, and QEP Extraction Pipeline.

*   **Week 2:** Query Execution Plan (QEP) to Directed Acyclic Graph (DAG) Parser.

*   **Week 3:** GNN Cost Predictor Model Training (Supervised Regression).

*   **Week 4:** Index Space Exploration & GNN-Guided Beam Search Algorithm.

**Month 2: The Engine (Validation, Backend, and Explainability)**

*   **Week 5:** `hypopg` Integration & The Validation Engine.

*   **Week 6:** FastAPI Backend Architecture & Orchestration.

*   **Week 7:** SHAP Explainability & Recommendation Scoring Engine.

*   **Week 8:** Frontend Dashboard & QEP Tree Visualization.

**Month 3: The Polish (Edge Cases, Metrics, and Demo)**

*   **Week 9:** Benchmarking, Ablation Studies, and Metric Calculation.

*   **Week 10:** Edge Case Handling (Conflicting indexes, write-heavy warnings).

*   **Week 11:** UI/UX Polish, Latency Optimization, and Bug Smashing.

*   **Week 12:** Documentation, Pitch Deck, and Mock Defenses.

---

###  The Milestone Explanations

#### Month 1: The Brain (Data, Graphs, and GNN)

**Week 1: Environment Setup, PostgreSQL Baseline, and QEP Extraction**

*   **What to do:** Spin up PostgreSQL and a lightweight UI (pgAdmin or DBeaver). Load a standard benchmark dataset (TPC-H or IMDB, scaled to 500k rows). Write a Python script using `psycopg2` to execute queries and extract the output of `EXPLAIN (ANALYZE, FORMAT JSON)`.

*   **Brutal Reality Check:** Do not waste time building a custom dataset. Use TPC-H. If you spend Week 1 scraping random SQL queries from GitHub, you will fail.

**Week 2: QEP to DAG Parser**

*   **What to do:** Write the parser that takes the PostgreSQL JSON output and converts it into a PyTorch Geometric (PyG) `Data` object. Nodes = operators (SeqScan, HashJoin). Edges = data flow. Node features = estimated rows, actual rows, cost, operator type (one-hot encoded).

*   **Brutal Reality Check:** Postgres JSON plans are messy and nested. You will spend 3 days just writing recursive functions to flatten the tree into a graph. Start this early.

**Week 3: GNN Cost Predictor Training**

*   **What to do:** Train a Graph Neural Network (GraphSAGE or GAT) to predict the *actual execution time* (or total cost) of the query plan based on the graph structure. This is a standard supervised regression task.

*   **Brutal Reality Check:** Do not use Reinforcement Learning here. RL is unstable and will eat your timeline. Train a supervised GNN to act as a "Learned Cost Estimator." It’s faster, stable, and mathematically sound.

**Week 4: Index Space Exploration & Beam Search**

*   **What to do:** Write the algorithm that generates candidate indexes. For a given query, identify filter/join columns. Generate single-column and composite index candidates. Use your trained GNN to score the "predicted cost" of each candidate and keep the top $K$ (Beam Search).

*   **Brutal Reality Check:** The index search space is infinite. If you try to brute-force it, your script will crash. Limit the beam width to 5 and max index columns to 3.

#### Month 2: The Engine (Validation, Backend, and Explainability)

**Week 5: `hypopg` Integration & The Validation Engine**

*   **What to do:** Install the `hypopg` extension in Postgres. Write the Python logic that takes the top candidate from Week 4, injects it as a *hypothetical* index, runs `EXPLAIN (FORMAT JSON)` again, and calculates the actual predicted speedup.

*   **Brutal Reality Check:** This is your "God-Tier" feature. If `hypopg` fails to install or your Python wrapper breaks, your demo is dead. Test this in isolation before connecting it to the rest of the app.

**Week 6: FastAPI Backend Architecture**

*   **What to do:** Wrap your Python scripts into a clean FastAPI application. Create endpoints: `/connect_db`, `/get_schema`, `/analyze_query`, `/get_recommendations`. Use WebSockets or SSE (Server-Sent Events) to stream the "Analyzing..." progress to the frontend.

*   **Brutal Reality Check:** Don't just use basic HTTP requests for the analysis endpoint. If it takes 2 seconds, the frontend will freeze. Stream the status updates.

**Week 7: SHAP Explainability & Scoring Engine**

*   **What to do:** Integrate SHAP (SHapley Additive exPlanations) for your GNN. Calculate which nodes (e.g., the HashJoin node) contributed most to the high predicted cost. Build the logic to format this into a readable JSON for the UI.

*   **Brutal Reality Check:** SHAP on graphs can be computationally heavy. Use a simplified gradient-based attribution or pre-calculate the SHAP values for your demo queries so the UI doesn't lag.

**Week 8: Frontend Dashboard & QEP Visualization**

*   **What to do:** Build the UI. Use React (or Streamlit if you are weak at frontend). The core feature is a visual tree renderer for the QEP. Show the "Before" tree in red, and the "After" tree in green.

*   **Brutal Reality Check:** A table of numbers is boring. The visual tree diagram is what gets you the A+. Use a library like `react-flow` or `d3.js` to render the JSON plan as a tree.

#### Month 3: The Polish (Edge Cases, Metrics, and Demo)

**Week 9: Benchmarking and Metrics**

*   **What to do:** Run your system against 50-100 queries. Calculate the metrics: Prediction Error (MAE), Recommendation Success Rate (how often did `hypopg` confirm the speedup?), and Latency. Compare your GNN's recommendations against standard Postgres heuristics.

*   **Brutal Reality Check:** If your GNN is worse than Postgres's native planner on some queries, *document it*. Panels respect honesty and edge-case analysis more than fake 100% success rates.

**Week 10: Edge Case Handling**

*   **What to do:** Add logic to detect conflicts. If Query A wants an index on `(A, B)` and Query B wants `(B, A)`, suggest a composite `(A, B, C)` or flag it for manual review. Add a warning if the target table is write-heavy.

*   **Brutal Reality Check:** This shows architectural maturity. It proves you aren't just building a toy, but a tool that understands real-world database trade-offs.

**Week 11: UI/UX Polish and Latency Optimization**

*   **What to do:** Make it look professional. Add loading skeletons, error states, and smooth transitions. Optimize your Python code so the end-to-end latency is under 1.5 seconds.

*   **Brutal Reality Check:** Judges judge books by their covers. If your UI looks like a 2010 Bootstrap template, they will assume your code is just as outdated.

**Week 12: Documentation, Pitch Deck, and Mock Defenses**

*   **What to do:** Write the final report. Build the slide deck. Practice the demo until you can do it in your sleep. Prepare for the "Gotcha" questions (e.g., "Why not just use AWS Performance Insights?").

*   **Brutal Reality Check:** Do not code this week. If you are still writing code in Week 12, you have already failed. This week is for storytelling and defense prep.

---

Stick to this. Do not add "cool features" in Week 6. Do not rewrite the parser in Week 9. Execute the plan.